## Project Update 2020
DATE COMPLETED | PROJECT NAME | DESCRIPTION | CONTRACTOR/SUPPLIER/CONSULTANT | FUNDING AGENCY | TOTAL COST
WATER
August 2025 | Salmon R. Road/Colbourne St.watermain to service TTO - Mohawk Language School | Installation of 200mm watermain on River Road and Colbourne St | Buildall Contractors/Greer Galloway | ISC - 100% | 344841.75
August 2025 | Ferry Lane - Water and Wastewater Servicing | Installation of 180m of 150mm watermain, 173m of 200mm sanitary main and one prefab liftstation with 15m of forcemain | Gordon Barr Ltd./Greer Galloway | ISC - 100% | 1013101
March 2024 | New Water Truck (2024) | Purchased new 2024 Freightliner truck and tank to replace 2009 water tanker for the water delivery program | Metro Freightliner and TransTank | ISC - 100% | 337310
May 2025 | QMS Interior Plumbing Upgrade Phases I and II | Replace interior copper piping and valves with pex and stainless steel valves. Phases I and II. | C & E Mechanical/FNES | ISC - 100% | 632253.84
September 2024 | Aquarius Tank Improvements - MBQ WTP | Refurbrish pretreatment and DAF tanks | Wilby Contracting/FNES | ISC - 100% | 635612
February 2024 | Bells Rd water and North Street water and sewer | Installation of 200mm watermain on Bells Rd and water and sewer on North Street | Scott Trudeau Construction/Greeg Galloway | ICIP - 93.33% MBQ - 6.67% | 4568295.34
October 2025 | Capacity Assessment - MBQ WTP & Deseronto System | Review system capacity to accommodate unserviced areas | FNES | ISC - 100% | 77280
|  |  |  | TOTAL | 7608693.93
WASTEWATER
October 2025 | Peatland Wastewter Treatment Expansion Design | Design additional peat cells, upgrade pumps and PLC | FNES | ISC - 100% | 67000
|  |  |  | TOTAL | 67000
ISC LOBBY RESULTS
January 2025 | Firehall Construction Cost Reimbursement | MBQ initiated New Firehall Construction bridging the construction costs. ISC reimbursed MBQ. | Buildall Construction/CKI Architects | ISC | 4323195
March 2025 | Phase II Cost Overrun Reimbursement | MBQ completed Phase II comprised of Water Tower and 8km Distribution. MBQ lobbied ISC for reimbursement of shortfall | Gordon Barr Ltd/FNES | ISC | 1018253
April 2025 | Phase IV Cost Overrun Reimbursement | MBQ completed phase IV comprised of 1.8kms of distribution.MBQ lobbied ISC for reimbursement of shortfall | Gordon Barr Ltd/FNES | ISC | 540839
|  |  |  | TOTAL | 5882287
NEW ROAD CONSTRUCTION
TBD | Homeland Drive | New Road Construction - 1.615km c/w watermain | Fidelity Engineering and Construction/Monument | ISC - 100%
| Eli's Lane South | New Road Construction - 1.15km c/w watermain | Fidelity Engineering and Construction/Monument | ISC - 100%
| Hickory Rd | New Road Construction - 0.5 km c/w watermain | Fidelity Engineering and Construction/Monument | ISC - 100%
| Marks Road - West | New Road Construction - 0.41km c/w watermain | Fidelity Engineering and Construction/Monument | ISC - 100%
| Milltown Rd - South | New Road Construction - 0.56km c/w watermain | Fidelity Engineering and Construction/Monument | ISC - 100% | 6880567.11
|  |  |  | TOTAL | 6880567.11
ROADS RECONSTRUCTION PROJECTS
December 2024 | York Road Phase III - Hwy #49 to Wymans Rd | Road Resurfacing from Wymans to Hwy #49. | Fidelity Engineering and Construction/ Q&E Engineering | ISC - 100% | 4943309.02
October 2025 | TTO - Salmon R. Road/Colbourne St. | Road Reconstruction | Buildall Contractors/Greer Galloway | ISC - 100% | 700133.25
|  |  |  | TOTAL | 5643442.27
CRACK SEALING PROGRAM
July 2025 | York Rd | Crack sealing program | Miller Group | ISC
| Meadow Drive | Crack sealing program | Miller Group | ISC | 52769.4
July 2025 | Huron Brant Drive North | Crack sealing program | Miller Group | ISC
| Oronhyatekha Drive | Crack sealing program | Miller Group | ISC
| Deserontoyon Dr | Crack sealing program | Miller Group | ISC
| Deyoronseh Dr | Crack sealing program | Miller Group | ISC | 22510.65
|  |  |  | TOTAL | 75280.05
MICROSURFACING
October 2025 | Huron Brant Drive North | Microsurfacing | Miller Group | ISC - 100%
| Oronhyatekha Dr | Microsurfacing | Miller Group | ISC - 100%
| Deserontoyon Dr | Microsurfacing | Miller Group | ISC - 100%
| Deyoronseh Dr | Microsurfacing | Miller Group | ISC - 100% | 101877.75
|  |  |  | TOTAL | 101877.75
SURFACE TREATMENT
August 2024 | Ridge Rd | Tar and Chip | Greenwood Paving | ISC
| Beach Rd | Tar and Chip | Greenwood Paving | ISC
| Milltown Rd | Tar and Chip | Greenwood Paving | ISC
| Hickory Rd | Tar and Chip | Greenwood Paving | ISC
| Norways Rd | Tar and Chip | Greenwood Paving | ISC
| Gordons Rd | Tar and Chip | Greenwood Paving | ISC | 665077
|  |  |  | TOTAL | 665077
SURFACE TREATMENT
September 2025 | Wymans Rd | Tar and Chip | Greenwood Paving | ISC
| Airport Rd | Tar and Chip | Greenwood Paving | ISC
| Toms Rd | Tar and Chip | Greenwood Paving | ISC
| Snookies Rd | Tar and Chip | Greenwood Paving | ISC
| Shannonville Rd - South | Tar and Chip | Greenwood Paving | ISC
| Norways Rd - South | Tar and Chip | Greenwood Paving | ISC | 473731.95
|  |  |  | TOTAL | 473731.95
SURFACE EMULSION
July 2024 | Church Lane South | apply surface emulsion | Superior Road Products | ISC
| Huron Brant Drive North | apply surface emulsion | Superior Road Products | ISC
| Beach Rd | apply surface emulsion | Superior Road Products | ISC
| Deserontyon | apply surface emulsion | Superior Road Products | ISC
| Deseronseh | apply surface emulsion | Superior Road Products | ISC
| York Rd | apply surface emulsion | Superior Road Products | ISC | 97412
|  |  |  | TOTAL | 97412
SURFACE EMULSION
September 2025 | Ridge Road | apply surface emulsion | Superior Road Products | ISC
| York Road - Norways to Upper Slash | apply surface emulsion | Superior Road Products | ISC
| Cedar Glen/Gussys Lane | apply surface emulsion | Superior Road Products | ISC
| Sero's Road | apply surface emulsion | Superior Road Products | ISC
| Airport Road | apply surface emulsion | Superior Road Products | ISC
| Beach Road | apply surface emulsion | Superior Road Products | ISC
| Mowbrays Rd | apply surface emulsion | Superior Road Products | ISC
| U. Slash Rd | apply surface emulsion | Superior Road Products | ISC
| Mohawk Rd | apply surface emulsion | Superior Road Products | ISC
| Iroquois Rd | apply surface emulsion | Superior Road Products | ISC
| Wellness Drive | apply surface emulsion | Superior Road Products | ISC
| Norways Rd | apply surface emulsion | Superior Road Products | ISC
| Sadies Lane | apply surface emulsion | Superior Road Products | ISC
| Billy Brew Rd | apply surface emulsion | Superior Road Products | ISC | 394156
|  |  |  | TOTAL | 394156
STREETLIGHT INSTALLATIONS
September 2024 | Streetlight Installations - Various locations (12) | Installation of solar lights | NRG Alternatives Ltd |  | 84885.5
December 2025 | Streetlight Installations - Various locations (8) | Installation of solar lights | NRG Alternatives Ltd |  | 61120
|  |  |  | TOTAL | 146005.5
STUDIES
June 2025 | QMS Building Assessment | Comprehensive Building Assessment | FNES | ISC - $30,000.00 | 30000
|  |  |  | TOTAL | 30000
ENVIRONMENTAL
Ongoing | Flood Remediation Property Repairs (2019) | In spring of 2019 MBQ experienced flooding due to high Bay levels. iSC provided funding to cover MBQ expenses. There are some properties still awaiting authorization to complete repairs. | Various/FNES | ISC - Emergency Services - $399,580.74 | 399580.74
August 2025 | Tree Removals - various roadways and properties | Ice Storm clean up | Butler Tree Service/Abbys Tree Removal | ISC Authorized Amount | 65000
|  |  |  | TOTAL | 464580.74
MISCELLANEOUS
Fall 2023 | Fire Truck Purchase | Purchase (2) triple combination pumpers | Battleshield Industries Ltd | ISC - $1,312,357.00 | 1312357
Ongoing | Waste Collection Truck Purchase | Purchase (2) Waste Collection trucks | Joe Johnson Equipment |  | 1006850.74
|  |  |  | TOTAL | 2319207.74
|  |  |  | Total all Projects | 30384738.3

## Future Projects
FUTURE INFRASTRUCTURE PROJECTS
CATEGORY | PROJECT NAME | DESCRIPTION | TOTAL COST
Water | New Watermain for Unserviced Areas | Installation of approximately 34km of watermain to the remaining unserviced areas. | 57669575
Water | Watermain Servicing L. Slash Rd/Mowbrays Rd/Clarence Rd/North Church Lane | Installation of approximately 6km of watermain. | 8766300
Water | MBQ Water Treatment Plant | Anticipating recapitalization of MBQ WTP to accommodate MBQ's water demand west of #49. | 30750000
Water | Deseronto Water Plant - Recapitalization | Anticipating recapitalization of the Deseronto WTP to accommodate MBQ's water demand east of #49. | 3000000
|  | TOTAL | 100185875
Wastewater | Peatland System Expansion | Construction of four additional peat cells, two wetland cells and subsurface granular mantle outfall system to meet the needs of the Sadie's Lane Housing Development. | 6152950
Wastewater | New Wastewater Treatment Plant | Construction of wastewater treatment plant to mitigate issues with residential septic systems ability to properly treat chlorinated wastewater in areas serviced by watermain distribution system | 30000000
Wastewater | Deseronto Wastewater Plant - Recapitalization | Anticipating recapitalization of the Deseronto WWTP to accommodate MBQ's wastewater demand east of #49. (ie pump upgrades, sludge storage management, primary, secondary and tertiary treatment optimization | 3000000
Wastewater | New Wastewater Collection System to Unserviced Areas | Eli's Lane from Hickory Road to Ridge Road, Ridge Road from Eli's to York Road, York Road from Community Centre to Meadow Drive. Total length of sanitary = 4.05km | 180000000
|  | TOTAL | 219152950
Roads | York Road - Norways Rd to Wymans Rd | Microsurfacing - approximately | 214711
Roads | Huron Brant Drive North Rehabilitation | Significant asphalt deterioration, wheel rutting and drainage issues. Proposing to pulverize 0.85km of ashpalt and replace with new. Drainage improvements. | 1275000
Roads | Huron Brant Drive South Rehabilitation | Significant asphalt deterioration, wheel rutting and drainage issues. Proposing to pulverize 0.8km of ashpalt and replace with new. Drainage improvements. | 1200000
Roads | Oronthyatika Drive Rehabilitation | Significant asphalt deterioration, wheel rutting and drainage issues. Proposing to pulverize 0.16 ashpalt and replace with new. Drainage improvements. | 240000
Roads | Deyronseh Drive Rehabiltation | Significant asphalt deterioration, wheel rutting and drainage issues. Proposing to pulverize 0.06km of ashpalt and replace with new. Drainage improvements. | 90000
Roads | Deserontyon Drive Rehabiltation | Significant asphalt deterioration, wheel rutting and drainage issues. Proposing to pulverize 0.14km of ashpalt and replace with new. Drainage improvements. | 210000
Roads | L. Slash Road Reconstruction | Existing conditions have deteriorated creating siginifcant public safety and liabilty issues for the First Nation. Base improvements required for 2.4km, drainage improvements and resurfacing with light butimous surface treatment. | 1800000
Roads | Church Lane North Reconstruction | Existing conditions have deteriorated creating siginifcant public safety and liabilty issues for the First Nation. Base improvements required for 1.4km, drainage improvements and resurfacing with light butimous surface treatment. | 1050000
Roads | Mowbrays Road Reconstruction | Existing conditions have deteriorated creating siginifcant public safety and liabilty issues for the First Nation. Base improvements required 1.0km, drainage improvements and resurfacing with light butimous surface treatment. | 750000
Roads | Wymans Rd Reconstruction | Existing conditions have deteriorated creating siginifcant public safety and liabilty issues for the First Nation. Base improvements required 3.3km, drainage improvements and resurfacing with light butimous surface treatment. | 2475000
Roads | Gordons Rd Reconstruction | Existing conditions have deteriorated creating siginifcant public safety and liabilty issues for the First Nation. Base improvements required 1.7km, drainage improvements and resurfacing with light butimous surface treatment. | 1275000
Roads | Upper Slash Road - west (York to Milltown) | Pulverize and resurface 1.7km with light butimous surface treatment. | 170000
Roads | Upper Slash Road - east (Norways to Wymans) | Pulverize and resurface 2.3km with light butimous surface treatment. | 230000
Roads | Beach Road | Pulverize and resurface 3.1km with light butimous surface treatment. | 310000
Roads | Ridge Road | Pulverize and resurface 6.1km with light butimous surface treatment. | 610000
Roads | Upper Slash Road | 1150m road extension | 1092500
Roads | Beach Road | 825m road extension | 783750
Roads | Church Lane N - Road Extension | 100m road extension | 95000
|  | TOTAL | 13870961
Bridges | Mud Creek Bridge Rehabilitation | OSIM identified the following: repair box girder ends, replace deck drains, repair concrete where required, replace joint seal | 700000
Bridges | Sucker Creek Bridge Rehabilitation | OSIM identified the following: repair girder ends, and repair concrete where required | 500000
Bridges | Mowbray's Road Bridge Rehabilitation | OSIM identified the following: miscellaneous concrete repairs where required and connect guiderail to structure | 100000
Bridges | Bells Road Bridge Rehabiliation | OSIM identified the following: waterproof and repave, repair barrel joints, repair concrete where required and attach guiderail to structure | 500000
|  | TOTAL | 1800000
Buildings | New Childcare Facility | Approx. 12,000 ft.2 new childcare facility to centralize Tahatikonhsotontie Headstart and Eksa'Okon:'a Childcare Centre, and expand into infant care. | 6689163
Buildings | Quinte Mohawk School Replacement | Originally constructed in 1974 QMS is approaching 60 years. Enrollment is increasing and there is inadequate classroom space and additions are no longer feasible. HVAC systems are aging and do not meet current standards to address pandemic recommendations. Technical assessment is required in support of replacement. | 30000000
Buildings | Educational Resource Centre | Construct new 10,000 sq ft facility to support Ohahase education programming and education administration services. For example, post secondary intake, Ohahase school curriculum delivery, and language coordinator services. | 6000000
Buildings | Indigenous Treatment Centre | Currently, facilities are limited in adjacent municipalities for members seeking treatment for addiction issues. Construction of a secondary building to house staff and counselling programming is required. Proposing to construct 2,500 sq ft building. Feasibility study required to asses the needs and type of facility. | 1650000
Buildings | New Public Works Storage Garage | Require 4-6 bay facility to house waste collection truck, water tanker, generators, grass cutting tractors, water and wastewater materials and other various equipment. 10,000 sq ft facility required. | 4200000
Buildings | New Business Centre 1 | construction of 11,000 ft.2 business centre which include 4 separte suites for commercial and administrative space to support local busiensses and adminstrative organizations looking for commercial space. | 4795341
Buildings | New Business Centre 2 | construction of 11,000 ft.2 business centre which include 4 separte suites for commercial and administrative space to support local busiensses and adminstrative organizations looking for commercial space. | 4795341
Buildings | Community Wellbeing Centre Secondary Building | A secondary building for the Social Programming of approximately 16,600 sq-ft (1,540 sq m) connected to the existing building by a Breezeway. The program included: 3 Departments (MFS, Goodminds, OW) with private print/copy station and coffee bar, Boardroom, Staff lounge/teaching kitchen, Workshop, Server room / General storage rooms / Janitors office / Janitors’ closet, Internal courtyard, Relocating the existing smoke structure, Relocating the existing play structure, Expanding the East parking lot | 8316000
Buildings | Medical Services Building Phase II | Construct 3,000 sq ft to house medical programming requirements. Existing facility has maximized current floorspace. Additional space is required. | 2000000
Buildings | Waste Transfer Depot | Building upgrade required to house staff and bathroom faciities. Hydro required. | 500000
Buildings | New Salt Storage Building | Currently storing sand and salt to together however limited space to ensure adequate salt volume for winter operations. Proposing to construct 2,500 sq ft salt shed. | 500000
Buildings | Christ Church Repointing | Repointing of the stone masonary at Christ Church Her Majesty's Chapel Royal of the Mohawk - National & Provincial Historial Site. 1 of only 5 Royal Chapels outside of Great Britain. | 2500000
Buildings | FNTI Office Building - Roof Replacement | Replace the existing roof at 3 Old York Road | 267600
Buildings | Ferry Lane Boat Launch | Replacment of the existing concrete boat launch loctaed at the end of Ferry Lane. Includes replacment of the launch abutment and floating dock. | 896000
Buildings | Arena / Multi-Sport Facility | Feasibility study stage. | 29747090
Buildings | Lacrosse Box Upgrades/Repairs |  | 311074
|  | TOTAL | 103167609
Electrification | Upper Slash Road - Road Extension Hydro Servicing | New hydro servicing for 1150m road extension | 230000
Electrification | Beach Road - Road Extension Hydro Servicing | New hydro servicing for 825m road extension | 165000
Electrification | Church Lane N - Road Extension Hydro Servicing | New hydro servicing for 100m road extension | 20000
Electrification | Homeland Drive - Road Extension Hydro Servicing | New hydro servicing for 1560m road extension | 312000
Electrification | Eli's Lane - Road Extension Hydro Servicing | New hydro servicing for 550m road extension | 110000
Electrification | New Hydro Servicing for Unserviced Areas | York Rd (East from Norways to 1096 York), Airport Rd (411 Airport Rd to Ridge Rd), Upper Slash Rd (#926 - #964). Total approximate length = 5.2 km | 1040000
|  | TOTAL | 1877000
Studies | Comprehensive Community Plan | Comprehensive Community Plan required to determine capital and programming resources in all MBQ operations and services delivered to the community. | 750000
Studies | Community Surface Water Drainage Study | MBQ has experienced wet weather events in 2017 and 2019 and are considered vulnerable to climate change impacts. As extreme weather events become more frequent, surface water drainage study is required to determine drainage areas to outlet ditching system | 250000
Studies | Road Needs Study | Study required to determine overall roads network and to develop logistical plan to address prioritized deficiencies. | 50000
Studies | OSIM Bridge Study | Recommended bridges assessed every 3-5 years for structural integrity and overall condition. MBQ commissioned the last study in 2019. | 20000
Studies | Wastewater Treatment & Collection Feasibility Study | MBQ has approximately 200 residential units serviced by our water treatment plant commissioned in 2016. Conventional septic systems typically have difficulty treating septage with the introduction of chlorinated water. Feasibility study required to determine wastewater primary and tertiary treatment alternatives and identify collection servicing phasing. | 300000
Studies | Structural Studies - Community Buildings | MBQ has approximately 30 exisitng buildings which need to be evaluated for code compliance, fire protection and HVAC pandemic compliance | 150000
Studies | QMS Technical Assessment | QMS is now approaching 60 years in service. Technical assessment of the interior and exterior structural components, fire protection compliance and HVAC pandemic standards and compliance | 120000
Studies | Indigenous Treatment Centre Feasbility Study | Feasibility study to determine office requirements to delive addiction treatment and counselling services to the community, | 50000
Studies | Educational Resource Centre Feasibility Study | Feasibility study to determine office requirements to deliver education services to the community, | 50000
Studies | Medical Services Building Phase II feasibility study | Feasibility study required to determine office requirements to deliver medical services to the community, | 50000
|  | TOTAL | 1790000